# TIRM Scoping

This document analyses the TIRM project and states the required hours to implement.

## Estimate

The project is estimated to take 51 days.  This includes a modest 25% overestimate for contingencies.  The project should take about 10 weeks on the calendar.

## Tasks

The current viewer design has the following major parts:

- Build viewer framework,

- Open a new or existing project,

- Select a Hazard Point,

- Select an Historic Event,

- Select a Source Zone,

- Select an Event, and

- Packaging.

### Build viewer framework

  - Create a framework to display ‘pages’ in a traditional 3-view display.  7 days.

### Open a new or existing project

  - Open an existing project and start the viewer “in the middle” of a project.  Also allow saving of project information.  2 days.

### Select a Hazard Point

  - Generate three levels of Australia map to allow hazard point selection.  5 days.

  - Generate data to implement a wave height to/from return period function.  3 days.

### Select an Historic Event

  - Create a page that allows user to specify lon+lat+radius.  1 day.

  - Fit this into the previously linear progression of pages (skips next page).  3 days.

### Select a Source Zone

  - Generate three (or more) levels of Indian plus Pacific oceans map to show source zones.  6 days.

### Select an Event

  - Generate display maps of events within a zone.  5 days.

  - Display a grid of events from the source.  Display a map of events in zone when requested.  4 days.

### Packaging

  - Put all files onto a sample external disk.  Test.  5 days.