## Sheet1
Workload 2004/2005: Chris, Ole, Duncan | [7 empty] | Last updated: |  | 2026-07-30
|  | Status | Ole | Duncan | Chris | Student | Stephen | Darran | Vanessa | Deliverables | Dependencies | Tentative Time frame | Description
Strong wind - tropical cyclone |  | Done | 5 |  | 2 | [5 empty] | None | Ongoing | Recruitment of suitable candiadte, interaction and handover of information
1. Storm surge hazard model development
| 1.1 Model Development | Done | 5 | 10 | 10 |  | 10 |  |  | First-order synoptic wind storm surge model |  | Sep 2004 - April 2005 | Further development of numerical model, software engineering, integration of forcing terms (tide and cyclone).
| 1.2 User Interfaces | On track |  | 10 | 3 |  |  |  |  | Ongoing | 1.13 | Sep 2004 - Mar 2005 | Development of user friendly interface to software.
| 1.3 Model description report | On track? |  |  | 10 |  |  |  |  | Report | None | 2004-09-01 | Description of physical, mathematical and numerical models for the storm surge hazard model.
| 1.4 User manual | % | 5 | 5 | [5 empty] | Report | 1.2 | Feb - Mar 2005 | Manual providing enough information to setup and run simulations.
| 1.5 Reference manual | % | 5 | 5 | [5 empty] | Report | 1.13 | 2005-02-01 | Document describing architecture of software.
| 1.6 Two papers on the comparison | % |  |  | 20 |  |  |  |  | Papers | 1.9,1.10,1.13,1.14 | 2004-12-01 | Reporting on the development, impementation of the first-order storm surge model to real data and analytical solutions.
| 1.7 Wave model | % |  |  | 5 |  | 10 |  |  | Ongoing | 1.1 | 2005-06-01 | Investigation into the implementation of a model to simulate waves in the storm surge model.
| 1.8 Alpha shapes | Done |  | 5 | 2 |  |  |  | 10 | Code | None | 2004-09-01 | Code integrated with pmesh providing a facility for computing a non-convex outline of a spatial dataset.
| 1.9 Data preprocessing/smoothing tool | Done | 5 | 10 | [5 empty] | Code | 1.13 | 2004-12-01 | Software for processing observed data. For example mapping data points at arbitrary locations to triangular vertices with a smoothing facility and the Douglas-Pucket algorithm for filtering boundary data..
| 1.10 Validation (Merimbula) | ? |  |  | 30 |  |  |  |  | Data | 1.1,1.9,1.10,1.13,1.14 | 2004-12-01 | Validation of model results against real data.
| 1.11 Momentum sink study | % | 5 |  | 3 | 25 |  |  |  | Ongoing (depending on external staff) | 1.13 | 2004-05-01 | Development of method for aggregating several buildings into one forcing term thus reducing the resolution required for a given study area.
| 1.12 Single proc version released for QC | % | 5 | 5 | [5 empty] | Code | 1.1,1.2,1.3,1.4,1.5,1.6,4.1 | 2005-04-01 | Release of first version of the storm surge model for quality control.
| 1.13 Refactoring for memory economy | Done | 15 | [6 empty] | Code | None | 2004-09-01 | Restructuring of code allowing resolutions of at least 300,000 triangular volumes.
| 1.14 Migration to beowulf cluster | % | 10 | [6 empty] | Code | 1.1,1.2,1.13 | 2005-06-01 | Implementation of model suitable for use with beowulf cluster
2. Modelling Framework
| 2.1 Input to framework | On track | 10 | [7 empty] | None | Ongoing | Interaction with work group in order to help define requirements and design of modelling framework for the DMAP project.
| 2.2 GIS integration | Done |  | 15 | [6 empty] | None |  | Acquiring and processing data from GA databases and run a number of test simulation using it.
3. Beowulf
| 3.1 Acceptance | Done | 4 | 5 | [5 empty] | Report | Beowulf cluster | 2005-06-01 | Verification of basic cluster functionality, measuremnt of performance parameters, stress testing and verification that real MPI project can succsfully execute.
| 3.2 User group | Done | 2 | [6 empty] | Ongoing | Beowulf cluster | 2005-06-01 | Form high performance computing user group.
| 3.3 MPI workshops | % | 4 | 5 | [5 empty] | Ongoing | Beowulf cluster | 2005-06-01 | Give a number of workshops on the use of clusters, parallel computing and code optimisation.
4. Visualisation
| 4.1 OSS development | Done | 5 |  |  |  |  | 10 |  | Ongoing | None | 2004-10-01 | Further development of visualisation tools to have better appearance, enhanced functionality and flexibility.
| 4.2 Application | Done | 5 | [6 empty] | Ongoing | 2.2, 1.10 | 2004-12-01 | Use with GIS integration and validation studies to provide detailed visualisations of results.
5. Social Vulnerability |  |  | 5 | [6 empty] | Ongoing | None | 2005-03-01 | Support and interaction with Anita Dwyer to further develop her work.
6. Direct loss |  |  |  | 5 | [5 empty] | Ongoing | None | 2005-06-01 | Based on requirements from Marry M. expand the current direct economic loss model.
7. Indirect economic loss |  |  |  | 10 | [5 empty] | Ongoing | None | 2005-06-01 | Contribute to model development for indirect economic losses for a range of natural hazards.
8. Bushfire |  | Done? |  | 10 | 5 |  |  |  |  | Report | None | 2004-09-01 | Bushfire assessment web site.
9. Spiro |  | On track | 5 | [6 empty] | Report | None | Jan 2004 - Jun 2005 | Generation of wavelet features of hydro acoustic signals and predictive modelling.
10. National Flood Map |  |  |  |  | 10 |  |  |  |  | Ongoing | None | 2005-03-01 | Generation of a very simple national flood hazard map
Totals |  |  | 100 | 100 | 100 | 25 | 20 | 10 | 10

## Chris plan for transfer
Work plan for Chris' transfer to Critical Infrastructures Project.
Chris to deliver
Date
2004-11-30 | Analytical solutions for pyvolution
2005-01-31 | Merimbula validation
2005-01-31 | Model description report
2005-01-31 | One Paper
Duncan/Ole to deliver
2004-11-21 | Interpolation software (Ole+Duncan+Stephen) | done
2004-11-21 | Wind field forcing term (Ole) | done
2004-11-21 | Tidal cycle boundary condition (Ole) | done
2004-11-21 | Set friction by regions (Duncan + Ole) | done
End of 2005 | Cyclonic forcing term