Project Proposal for 2006 Graduates

| Division | Geospatial and Earth Monitoring |
| --- | --- |
| Project Name | Modelling the observed effects of the 1953 tsunami on Suva, Fiji |
| Overview of Project | Impacts to the built environment from natural hazards such as riverine flooding, storm surges or tsunami are critical in understanding the economic and social effects on our communities. In order to simulate the behaviour of water flow from such hazards within the built environment, Geoscience Australia has developed a hydrodynamic model suitable for modelling tsunami inundation. Validation of ANUGA has been successfully carried out using laboratory data from a simulation of the Okushiri 1993 tsunami. However, a validation against full scale run up observations have not yet been attempted due to difficulties sourcing adequate data. Recently, GA was given a dataset from such a validation of the Suva 1053 tsunami from Tariq Rahiman from university of Cantebury, New Zealand. The Suva tsunami of 1953 originated from a submarine landslide and it is well constrained, by bathymtery data, field mapping and historical records. There are useful historical data available from eyewitness accounts on well located coastal arrival times and run-ups. The bathymetry of the area, especially the intricate systems of nearshore lagoons, is well resolved. Suva also provides a test for complex wave interactions (shoaling, focussing effects etc) with the barrier reef system and deep reef passages. Tariq Rahiman has been submitted his work for publication but has agreed for us to reproduce the validation using ANUGA. This project will investigate if the observations can be modelled using the ANUGA model simulating the event starting with the landslide and propagating the non-linear wave onshore using the supplied data. . |
| Background to Project | The Risk Research Group with GEMD is developing numerical models as part of its commitment to assess the risks associated with rapid onset natural hazards within Australia. One of the hazard models being developed is ANUGA. It is a sophisticated numerical model based on the Shallow Water Wave equation which describes the movement of water in an arbitrary geometrical domain such as the bathymetry of a coastline, an estuary or within a built environment. |
| Nature of Proposed Work | - Familiarisation with the ANUGA model - Familiarisation with the Suva `53 data and validation work carried out by Tariq Rahiman - Create triangular mesh for an area covering the study area - Run ANUGA and compare modelled results to existing results - Adjust input parameters to obtain a better fit between observations and the model results if necessary. |
| Products to be Delivered | A report detailing the findings of the validation exercise. Present outcomes to GA. |
| Experience/Skills Required | A general geoscience background or hydrology. Computer literacy is essential, and Python programming skills would be an advantage. |
| Developmental Benefits | The outcomes from this proposed study will contribute to the development of an Australian tsunami risk and hazard map and assist the Australian Tsunami Warning System in understanding the exposure of the Australian coast. This risk map is an integral element for the Federal and State Governments approach to risk management. By working closely with members of the Risk Assessment Methods and Earthquake and Tsunami Hazards projects, the graduate will develop an understanding of the overall goals and issues with the national disaster mitigation project (DMAP) as well as the Australian Tsunami Warning System. Other benefits include: exposure to hydrodynamic modelling, Python programming language, sound software development practices and increased knowledge of the physical properties of tsunami and earthquakes. |
| Timeframe/Rotation | 2006 rotation |
| Resources and Funds Required | Standard GA workstation. |
| Supervisors | Ole Nielsen |
| Additional Project Advisors | Tariq Rahiman |

Proposal Approved:

(Chief of Division to complete)

_________________________________   ____ / ____ / ____

(Signature)