Process for production development of decision support tool for given client

- Client to nominate priority areas (eg, FESA, NSW DNR and SES, Tas SES). Note that GA can assist this process by provision of hazard maps and other available scientific information.

- Inundation modelling team to develop data extents and issue to NM&I and PMD.

PMD:

- Source available offshore data sets and issue to NM&I (with metadata) for DEM creation and lineage/metadata document (assuming database not already complete)

- Determine tidal range: Highest Astronomical Tide (HAT) and Lowest Astronomical Tide (LAT) from Australian National Tidal Tables all adjusted to AHD and issue to RAMP/inundation modelling team and NM&I.

NM&I:

- Develop DEM;

    - Source onshore data with given extent

    - Adjust offshore data from PMD to AHD if required

    - Combine offshore and onshore data

    - QC with available total station survey data as absolute ground truthing

    - QC by drawing HAT and LAT contour lines and test with time stamped imagery, geomorphology information and common sense.

    - Demonstrate QC activity by (1) measuring difference between DEM and spot elevations and other survey information and (2) issuing contour lines.

- Issue jpg image of HAT, LAT and MSL contour lines overlaid on aerial photography to inundation modelling team for inclusion in report. Image size required to be 300-400Kb in size.

- Issue offshore data sets as points file, coastline polygon as points file, and onshore data as ASCII grid (or points if available) to inundation modelling team for model development.

- Issue shapefiles of bathymetric and topographic contours (in 5m increments). This will be used by the modellers to develop interior polygons.

- Issue shapefiles of bathymetric and topographic clipping polygons. This will be used by the modellers to set initial conditions.

- Create lineage/metadata document and issue to inundation modelling team for inclusion in report.

- Report on licence agreements to RAMP/GIS team.

- Issue image of data extent (onshore and offshore) to inundation modelling team to assist with model development.

NM&I and RAMP/inundation modelling team:

- Determine points of interest for developing time series (onshore; hospitals, schools, power stations, airports etc and offshore; to demonstrate wave amplitude in approach). Engage with FESA and local representatives to determine additionally points of interest, particularly local icons.

- Create jpg image showing these point locations with elevation to two decimal places (no title required) on aerial photography and issue to inundation modelling team for inclusion in the report. Image size required to be 300-400Kb in size.

Earthquake and Tsunami Hazards Project:

- Provide output from hazard maps (MOST or URS) for region as boundary condition for inundation modelling.

RAMP/Inundation modelling team:

- QC DEM.

- Ensure one UTM zone for boundary input.

- QA/QC elevation data used for boundary condition with provided DEM.

- Cross-validate DEM to determine appropriate smoothing parameter, alpha.

- Set initial conditions to ensure that stage = 0 onshore. (Use clipping polygons from NM&I.)

- Create coarse model for study area using ET&H boundary condition information and supplied DEM.

- Export ASCII grid to NM&I for validation.

- Once internal regions and cell resolutions are adequate, simulate scenario on fine mesh.

- Determine maximum inundation depth for HAT, LAT and MSL scenarios.

- Export ASCII grids to RAMP/GIS team to develop inundation maps and decision support tool

- Source NBED information for study area. Append column (with name SHORE_DIST) which calculates the distance from coastline, in metres. Ensure locations lie in one UTM zone only.

- QC by loading NBED output and GNAF into ArcMap for verification.

- Determine damage estimates for HAT, LAT and MSL scenarios.

- Export damage modelling outputs at NBED locations to RAMP/Engineering team to develop casualty estimates

- Develop report; include lineage/metadata document and images from NM&I and casualty estimates from RAMP/Engineering team.

- Develop visualisation on chosen scenario

RAMP/GIS team:

- Develop inundation maps and decision support tools

- Report on licence agreements for all GIS layers.

RAMP/Engineering team:

- Develop casualty estimates based on damage modelling outputs

PMD outputs:

- Provision of best available offshore data with accompanying metadata

NM&I outputs:

- QC’ed DEM

- jpg image of HAT, LAT and MSL contour lines overlaid on aerial photography

- jpg image of chosen point locations overlaid on aerial photography

- image of data extent for region

- image detailing 0.5-1m contour lines

- Lineage/metadata documentation

RAMP outputs:

- Decision support tool

- Visualisations

- Impact estimates

- Report

E&TH Project outputs:

- Hazard maps

- MOST output

- URS output