Process for production development of decision support tool for given client

- Client to nominate priority areas (eg, FESA, NSW DNR and SES, Tas SES). Note that GA can assist this process by provision of hazard maps and other available scientific information.

- Inundation modelling team to develop data extents in consultation with ET&H, NM&I and PMD and issue to NM&I and PMD for data acquisition purposes.

PMD:

- Source available offshore data sets and issue to NM&I (with metadata) for DEM creation and lineage/metadata document (assuming database not already complete)

- Determine tidal range: Highest Astronomical Tide (HAT) and Lowest Astronomical Tide (LAT) from Australian National Tidal Tables all adjusted to AHD and issue to RAMP/inundation modelling team and NM&I.

NM&I:

- Develop DEM;

    - Read GA_Datum_Projection_standards.doc in this directory

    - Source onshore data with given extent

    - Adjust offshore data from PMD to AHD if required

    - Combine offshore and onshore data

    - QC with available total station survey data as absolute ground truthing

    - QC by drawing HAT and LAT contour lines and test with time stamped imagery, geomorphology information and common sense.

    - Demonstrate QC activity by (1) measuring difference between DEM and spot elevations and other survey information and (2) issuing contour lines.

- Issue jpg image of HAT, LAT and MSL contour lines overlaid on aerial photography to inundation modelling team for inclusion in report. Image size required to be 300-400Kb in size.

- Issue offshore data sets as points file, coastline polygon as points file, and onshore data as ASCII grid (or points if available) to inundation modelling team for model development.

- Create lineage/metadata document and issue to inundation modelling team for inclusion in report.

- Issue shapefiles of bathymetric and topographic contours (in 5m increments). This will be used by the modellers to develop interior polygons.

- Issue shapefiles of bathymetric and topographic clipping polygons. This will be used by the modellers to set initial conditions.

- Report on licence agreements to RAMP/GIS team.

- Issue image of data extent (onshore and offshore) to inundation modelling team to assist with model development.

- Issue image showing 0.5-1m contour lines to inundation modelling team to allow interpretation of model output.

NM&I and RAMP/inundation modelling team:

- Determine points of interest for developing time series (onshore; hospitals, schools, power stations, airports etc and offshore; to demonstrate wave amplitude in approach). Engage with FESA and local representatives to determine additionally points of interest, particularly local icons.

- Create jpg image showing these point locations with elevation to two decimal places (no title required) on aerial photography and issue to inundation modelling team for inclusion in the report. Image size required to be 300-400Kb in size.

Earthquake and Tsunami Hazards Project:

- Provide output from hazard maps (MOST or URS) for region as boundary condition for inundation modelling.

- The URS files will have the following attributes;

  - There will be 3 files: [base name]_waveheight-z-mux, [base name] _velocity-e-mux and [base name] _velocity-n-mux containing relative height, x-velocity and y-velocity, respectively.  The base name must be the same for all three files.

  - The velocity is given in m/sec, being positive in the Eastern direction for the –e-mux files and positive in the Southern direction for the –n-files.

  - The depth will be given in metres, with area’s of land being negative and sea being positive.

RAMP/Inundation modelling team:

- Input to DEM generation:

    - Define polygon of boundary region and give to geospatial scienceists to get elevation data and to geophysicists to get the boundary conditions.

    - Know the scenario zone and ensure it is contained in one UTM zone for boundary input.

    - Consider what grid resolution is required in which areas. This will reduce space required to store data and modelling time due to the number of points needed to load. For example having a 10x10m (asc) grid in area where the triangle resolution is 50000m2 triangle is very computational expensive, a 200x200m is much more appropriate and 400 times smaller! As a rule there should be a minimum of 3 points per triangle. This can be done easily with asc files as you know the grid resolution and you know what resolution is in the mesh. Consider using ‘geospatial_data’ ‘split’, ‘clip’ and ‘clip_outside’ to make smaller but accurate elevation files. This is done in the build script.

    - The build script (eg \anuga_work\production\broome\build_broome.py) is used to do one offer file conversion for ANUGA. Mainly the converting, adding and exporting of the ‘raw’ elevation data and conversions of the URS/MOST boundary conditions into SWW file.

    - Only reduce the asc grid resolution in areas which we are not exporting the results and reporting on them. This is due to two reasons, reducing the resolution of the data will increase the impact as it will smooth the slopes and 2 we are reporting we are using “best available” data and if we reduce the resolution we will not be using all the best available data.

    - Need to know the areas of interest to be able to determine if the elevation data provided is enough. It is very helpful to review NEXIS data in this area. Also ask if there is any tide gauges, anecdotal evidence or other area of interest. This will allow you to determine where to refine the model through using polygons.

    - If there are areas without data, consider inferring from a TIN. This involves using ArcGis to interpolate from what is available and make a raster which is then exported at a suitable resolution. Note, select resolution carefully.

    - Ask for a HAT line from GIS

- Get boundary condition

    - Use ‘run_boundary_points.py’ file found in broom example. It is very straight forward, it uses a function “URS_points_needed_to_file found in anuga.shallow_water.data_manager

    - How was the boundary condition source determined? What is the water depth of the point NM&I are using to determine maximum water height, or should their be an equation of water height and momentum, average of 5 point with water depth greater than 50m

- QC boundary condition

    - Check elevation data used for boundary condition with provided DEM.

    - Compare timeseries from a point very close to the model boundary from the boundary condition and ANUGA evolved model to confirm that the boundary condition is being used correctly. (could use boundary_plot or sww2csv_timeseries)

- Mesh Generation:

    - What are the areas of interest? Look at Nexis data, is there areas with recorded run-up, what elevation features should be resolved, cliffs, islands, inlets.

    - It is important to have a good mesh resolution in areas around islands that are between the earthquake source and the areas of interest. Also along the coast as reflections can be significant. An easy way to make complex polygons around the coast and island is to use ARCGIS, display contours like the -20m and 20m contour. There are instructions in svn covering this see, anuga_core/source/documentation/user_manual/ How to develop a polygon for scenario models using ArcGIS.pdf’

    - Create polygons considering the above and river inlets, coastal regions and low lying areas. Start from 100,000/150,000 meters squared (boundary) then to 20000 near the coast and areas of interest, then to 500 m in the areas of interest. Use arcgis and load up perth_polygon.mxd.

    - Check number of triangle when res_factor is 1 by using ‘number_mesh_triangles’ (generally this is in the project file), if too much over 500000 consider resizing polygons or boundary.

    - Once internal regions and cell resolutions are adequate, use “res_factor” to 10 to model a coarse mesh, inspect using swollen/anuga_viewer. If it looks good change res_factor to 1 and see how many triangle there are and if it look good.

    - Further you can check mesh resolution is correct using “graphical_mesh_interface.py” in pmesh

    - If necessary create an Initial Condition polygon that covers any area onshore that is below the HAT level and use these polygons to set the stage to less than the MSL or maybe LAT? If provide with a polygon for this function check it by running a coarse model with stage =1000 or plot IC.csv in excel.

    - clip in geospatial_data dies mysteriously with no error message

- QC Digital Elevation Map (DEM):

    - build a mesh at MSL and visually inspect in swollen for problems,

    - Cross-validate DEM to determine appropriate smoothing parameter, alpha.

    - export a grid(s) in areas of interest and give to GIS to QC. (Export ASCII grid to NM&I for validation.)

    - Are there any positive bathymetry points?

- Create fine model for study area using ET&H boundary condition information and supplied DEM.

- Analysis and export data

    - Determine maximum inundation depth for HAT, LAT and MSL scenarios. Use data_manager.get_maximum_inundation_data()

    - Export ASCII grids to RAMP/GIS team to develop inundation maps and decision support tool, might need to make rasters first and mosaic together. Use ‘shallow_water.data_manager  export_grid’

    - To Make the clip_depth and speed rasters from arcGIS (ascii to raster for each ascii file that contain data, then mosaic to new raster, then extract by mask using the topo clip to get the clip_depth. Note cos the speed raster doesn’t have the “extract by mask” stage it also need to have the “projection defined” correct, otherwise this might cause problems later

    - Determine damage estimates for HAT, LAT and MSL scenarios.

- Source NBED information for study area. Append column (with name SHORE_DIST) which calculates the distance from coastline, in metres. Ensure locations lie in one UTM zone only.

- QC by loading NBED output and GNAF into ArcMap for verification.

- Export damage modelling outputs at NBED locations to RAMP/Engineering team to develop casualty estimates

- Develop report; include lineage/metadata document and images from NM&I and casualty estimates from RAMP/Engineering team.

- Develop visualisation on chosen scenario

RAMP/GIS team:

- Develop inundation maps and decision support tools

- Report on licence agreements for all GIS layers.

RAMP/Engineering team:

- Develop casualty estimates based on damage modelling outputs

PMD outputs:

- Provision of best available offshore data with accompanying metadata

NM outputs:

- QC’ed DEM

- jpg image of HAT, LAT and MSL contour lines overlaid on aerial photography

- jpg image of chosen point locations overlaid on aerial photography

- image of data extent for region

- image detailing 0.5-1m contour lines

- Lineage/metadata documentation

RAMP outputs:

- Decision support tool

- Visualisations

- Impact estimates

- Report

E&TH Project outputs:

- Hazard maps

- MOST output

- URS output