Australian Government

Geoscience Australia

Draft Scoping for:

Tsunami Risk Modelling Activity (TRMA)

Produced by:	Ole Nielsen (Activity Leader – Risk and Impact Analysis Group)

Paul de Ruyter (Business Analyst - GEMD)

| Version | Date | By | Key Changes |
| --- | --- | --- | --- |
| 1.0 | 27 August 2007 | Paul de Ruyter | Initial Draft |
| 1.1 | 3 December 2007 | Ole Nielsen | Added section on priorities and some editorial changes. |
| 1.2 | 1 April 2008 | Jane Sexton and Ole Nielsen | Major review of priorities and resourcing. Removed activity list. |

| PROJECT TITLE | Tsunami Risk Modelling Activity |
| --- | --- |
| DIVISION/GROUP | GEMD |
| ACTIVITY LEADER | Ole Nielsen |
| PROJECT LEADER | Trevor Dhu |
| TRIM FILE NO. | D2007-140102 |

| BACKGROUND | This activity addresses the Tsunami Risk Modelling component of the Natural Hazard Impacts Project (NHIP) that is underpinned by the COAG reforms for natural disasters, particularly: - Reform Commitment 1 - develop and implement a five-year national project of systematic and rigorous disaster risk assessments. - Reform Commitment 2 - establish a nationally consistent system of data collection, research and analysis to ensure a sound knowledge base on natural disasters and disaster mitigation. This activity is funded through a variety of external agencies including, EMA, FESA, AusAID, JATWC and internally through the Geoscience Australia appropriation fund. |
| --- | --- |

| STRATEGIC ALIGNMENT | This activity is aligned to the following corporate strategic goals: - Deliver high quality, high priority geoscience information - Deliver innovative solutions to stakeholders - Continually improve business processes. This activity is being developed within the Geoscience Australia (GA) Natural Hazard Impacts Project (NHIP). The activity is an important component in the Australian Government’s Critical Infrastructure Protection initiatives including the CIPMA Program. |
| --- | --- |

| PURPOSE and OUTCOMES | The Tsunami activity aims to: - provide the Australian Government and public with a better understanding of tsunami risk in Australia by having a well rounded, mature, tsunami modelling methodology, that is documented, validated and published; - inform emergency management planning for tsunami in Australia and the region. The key beneficiaries of the outcomes are: - the Australian emergency management community, Commonwealth and State agencies; - the Joint Australian Tsunami Warning Centre (JATWC), a collaboration between Bureau of Meteorology (BOM), Emergency Management Australia (EMA) and GA; - planning arms at all levels of Australian Government, Commonwealth, State and Local (LGA’s); - regional Governments through AusAID; - national and international academia and scientists. |
| --- | --- |

Tsunami Modelling Process

STAKEHOLDERS

| OUTPUTS | Outcomes will be achieved by creating validated tsunami risk outputs by the following activities: - Gaining a better understanding of recurrence of tsunamigenic earthquakes, submarine landslides, and volcanic events in the region, with impacts on Australia and the region; - Gaining a better understanding of the mechanism of tsunamigenic sources; - Understanding how tsunami waves are created; - Understanding tsunami propagation and inundation; - Understanding the impact of tsunamis on marine and coastal environments; - Understanding model sensitivities; - Developing and validating all activity outputs; and - Creating and presenting hazard and risk maps. |
| --- | --- |

| PRIORITIES and DECISION POINTS | Priorities as of November 2007 - Year 7/8: - Delivery of National Probabilistic Tsunami Hazard map as funded by EMA - Validation of end-to-end tsunami modelling methodology and its components - Work on model sensitivities (e.g. bathymetric site classes, reef effects, generalisations etc) - Publications submitted - FESA risk modelling project underway (to be delivered by Dec 2008). - Decision to be made by June 2008: Are the models used sufficiently valid to reliably estimate the extent of inundation from a tsunami generated by an earthquake? This includes an estimate of the adequate horizontal resolution of elevation data. - Decision made in January 2008: Tsunami Risk is a national priority that GA should pursue regardless of external funding. In particular, pursuing the potential for a Mega-tsunami on the east coast has not yet been done and could become part of a GA program. - Year 8/9 (If models are insufficient) - Work out what needs improving and whether it is even possible to make the models sufficiently valid. Program would then follow a similar process to that outlined below, shifted by at least one year. - Year 8/9 (If models are considered valid and resources are available) Since tsunami is a national priority and the tsunami risk modelling methodology is adequate – a study to assess the potential for mega-tsunamis in Australia can be undertaken. - Select regions and communities that are candidates for catastrophic tsunami impact based on the National Probabilistic Hazard map and conduct further impact studies e.g. on the NSW coast. These studies should include volcanic and landslide events in addition to catastrophic tsunamigenic earthquakes. - The above will require literature review, development and testing of landslide and volcanic source functions. - Carry out further palaeotsunami work in regions that appear at risk to catastrophic tsunami impacts. - Combine model results, evidence from the palaeotsunami sub-activity and general tsunami science to form a position on the possible scale of tsunami events in Australia. - Develop capacity building projects such as: - Tsunami Impact Modelling Online Service (TIMOS) - Australian Tsunami Online Delivery Framework - Publicly released hydrodynamic modelling software - Decision to be made by June 2009: Is there a potential for catastrophic tsunami events in Australia? - Year 9/10 (If catastrophic tsunami events are considered unlikely) - Wrap up tsunami activity: See publications through, maintain capability for use by others, document what was done, finish palaeotsunami studies etc. - Look to other applications of hydrodynamic modelling (dam breaks, flooding, storm-surge) as required. - David Burbidge to get back into earthquake science. - Ole Nielsen will become an earthquake modelling expert overnight. - Jane Sexton to take over volcano risk activity. - John Schneider to become asteroid modelling expert. - Kristy van Putten to become flood modeller. - Year 9/10 (If catastrophic tsunami events are regarded a possibility) - Start the development of the next generation modelling methodologies. - Conduct studies using the URS model to predict tsunami waves at the coastline (where bathymetry is available). - Transition the tsunami modelling methodology to an operational context by way of TIMOS for use with next generation ATWS warnings. - Ultimately, work towards a National Tsunami Risk Map. |
| --- | --- |

| RESOURCING | The program outlined above will require: Staff Senior computational scientist: 1 FTE Responsible for the numerical models and the activity Tsunami earthquake hazard modeller: 1 FTE Responsible for modelling earthquake generated tsunamis Mathematical modeller: 1 FTE Responsible for developing landslide and volcanic generated tsunamis and exploring model responses to the coastal morphology. Software engineer: 1 FTE Responsible for continued maintenance and development of software underpinning this activity. Computational modeller: 1 FTE Responsible for the delivery of tsunami risk products to stakeholders as well as geophysical assistance within the activity Palaeotsunami scientist: 1 FTE Responsible for bringing historical and palaeontological evidence to bear on the national understanding of tsunami risk. Equipment: Access to computational resources such as the GA Beowulf clusters Access to ~20TB tiered storage Access to network Access to appropriate IT governance |
| --- | --- |

| INFORMATION MANAGEMENT IMPLICATIONS | Up to date, accurate topographic and bathymetric data and metadata to a high resolution is of high importance for modelling and in locating survey sites (including pre and post event elevation datasets).These could be obtained, formatted, QA’d and hosted?/managed within GA or retrieved directly from external agencies on demand. Survey datasets (post event and palaeo) will need to be identified, retrieved and possibly hosted in GA’s Located Sample Data (LSD) SPOT. Need to have access to new and historical DART buoy data. - Pacific – already available on the Internet. - Indian Ocean - due to be implemented 2007-09. Access to and management of raw tide gauge data and metadata from all regional sources (Bureau and State gauges). Access to and management of wave tank experimental data into archived and traceable datasets. There is a need to ensure that access to software repositories is available to external collaborators and vice versa, the activity has access to external repositories. |
| --- | --- |

| OUTPUT QA | There are and will be a variety of models and datasets in use during this activity. This activity will comply with the Model Input/Output Tracking System (MITS) project aims. The core aim of MITS is to develop processes and methodology that ensure model outputs are assured and reproducible. The FESA ANUGA deliverables will be used as the prototype of the MITS project. All validation work will be reproducible and published. |
| --- | --- |

| ASSUMPTIONS | The GA IT hardware environment improves in speed, performance and capacity over time as per expected normal advancements – (To enable advanced computation models to run faster and allow all model outputs and input data to be stored). IT governance changes in order to support scientific endeavour – I.e. at prototyping phase, access to datasets and models externally and internally have less restrictions to stored “live output” data and models. Access to data from other Government agencies is forthcoming and is meaningful? (e.g. elevation, survey and tide data) There is continued Government requirement of tsunami hazard and risk assessments. |
| --- | --- |

| CONSTRAINTS | Existing corporate structures and governance. “Lack of” IT support for computational clusters. IT infrastructure capabilities. Staff skill sets in respect of planned activities. Security procedures within IT environments. Licence conditions of inputs (maps, data and software) used to produce outputs on behalf of clients. Licence conditions of GA outputs (maps, data and software) produced for specific purposes on behalf of clients. Availability, accessibility and quality of data (e.g. survey, topography, bathymetry and tide). Client requirements Time Budget Resources |
| --- | --- |

| RELATED PROJECTS | - ATWS – shares data – uses some outputs? - EVP - provides engineering vulnerability curves. - NEXIS project – provides exposure data. - MITS project – provides direction and governance for model and database development. - CIP Scenario Modelling – require hazard and risk outputs - Web Redevelopment project – outputs are publicised through the web. - PMD: - marine surveys – provide survey data and priorities of where to model (e.g. submarine landslide identification and recurrence), - facilitate retrieval of bathymetry data, - facilitate acquisition and analysis of core samples. - National mapping – provide and facilitate retrieval of onshore elevation data and provide expertise on building elevation data sets suitable for inundation modelling purposes. - Variety of risk modelling activities through NHIP as outputs of these projects contribute to overall Australian Natural Hazard Risk Map. |
| --- | --- |

| DURATION | Start: Already started | End: July 2010 |
| --- | --- | --- |

| ESTIMATED COST | GA operational budget provides funding. Item; 2007/8; 2008/9; 2009/10. Staff. Hardware. Software. Data. Fieldwork. Travel. Conferences. Courses. Other. Total. |
| --- | --- |

| ESTIMATED ONGOING COST |  |
| --- | --- |

| INITIAL RISK IDENTIFICATION | Likely | Chance | Not Likely | Mitigation actions |
| --- | --- | --- | --- | --- |
| Failure to resource, recruit and retain staff. | 4 |  |  | GEMD are currently developing a workforce plan in order to recruit and retain staff in critical areas of expertise and duplicating critical skill sets. |
| Failure to manage and maintain data and systems. | 4 |  |  | GEMD IM are in the process of becoming operationally capable. |
| Inability to get access to external jurisdictions to further palaeo work. | 3 |  |  | Create a business case that advises GA senior executive of the importance of collaboration with international and national jurisdictions with a purpose to gain access to specific sites for tsunami research. |
| Peer reviews do not uncover methodology issues that could delay the activity |  | 4 |  | Publish, collaborate, validate and peer review at every phase of development. |
| Failure to manage new and existing stakeholders both in capacity to service and retain. |  | 3 |  | Tasks to be created within the activity that identifies likely output support services, management of client relationships and subsequent strategic planning. |
| Conflicting requirements between clients. |  | 3 |  | Strategic planning identifies priorities. |
| Failure to obtain accurate data | 3 |  |  | Investigate availability of appropriate data, create business case for obtaining and managing data. |
| Failure to manage IT support and procurement. | 4 |  |  | ISB are reviewing current policies, governance and processes in line with GA strategic directions. |
| Failure to validate outputs. |  | 4 |  | Publish, collaborate, validate and peer review at every phase of development. |
| Incorrect usage of output information by external users. |  |  | 5 | Disclaimers on outputs |
| Failure to correctly scope, plan and manage project. |  |  |  | Appropriate project planning |
| Failure to receive support from executive. |  |  | 5 | Appropriate project planning and communication of project goals and achievements. |
| Key - 5 = Critical to activity success 1 = Not critical to activity success |  |  |  |  |

| OTHER ISSUES | - The activity requires scheduled development and maintenance to ensure models are kept up to date and useful. - This activity is subject to prioritisation based on currency of the hazard. Tsunami may be seen to be not such a big hazard if there are no more international events in the near future (2-3 years). |
| --- | --- |

| SIGN OFF |  |  |
| --- | --- | --- |
| ---------------------------------------------------------- |  | ----------------------------------------------------------- |
| Project Leader |  | Date |
| VERIFICATION | The Divisional Information Manager verifies that this scope meets IM requirements and a Project IM plan has been developed. |  |
| ---------------------------------------------------------- |  | ----------------------------------------------------------- |
| Divisional Information Manager |  | Date |
| VERIFICATION | The Group Leader verifies that this scope meets stakeholder and other requirements. |  |
| ----------------------------------------------------------- |  | ---------------------------------------------------------- |
| Group Leader |  | Date |