Sensitivity Testing on Input Bathymetric Data for Inundation Modelling Purposes

Jan – Jun 2007

Aim

To determine characteristics for bathymetric data suitable for inundation modelling to inform stakeholders for further data acquisition exercises.

Plan

Use Onslow as a case study as (a) data coverage is “good” and (b) reasonable inundation was found. Other case studies will be included as time permits as a range of different bathymetric profiles will need to be investigated.

The initial investigation will focus on using existing data sets and varying the data coverage. Further investigation will look at incorporating uncertainty. This study will not look at convergence due to varying cell resolutions.

- Determine a range of points to measure inundation height,

- Fix the model’s mesh size over the selected points,

- Use a simple boundary condition to allow quick simulation,

- Baseline the inundation extent and values at selected points with the current data set,

- Use split method to progressively reduce the number of bathymetric data points used and record the inundation extent and values at selected points,

- Use the 250K data set and record the inundation extent and values at selected points,

- Describe the change in inundation extent and values as the data set changes.

Outputs

Report describing the effect of bathymetric data resolution on inundation in the Onslow region (and other regions as time permits).

Outcomes

- Increased knowledge in the modelling community

- Better informed stakeholders